## Tabelle1
Datum | Stunden | Aufgabe | Kommentar
2023-08-08 | 2 | Gebiete suchen | geschätzt | Summe | 496
2023-08-09 | 1 | Mail schreiben | geschätzt | Expected | 750
2023-08-24 | 3 | Thema einlesen | geschätzt | Percent | 66.13%
2023-09-08 | 1 | Meeting | geschätzt | ECTS | 19.84
2023-09-09 | 4 | Einlesen Themen | geschätzt
2023-09-15 | 3 | Einlesen Themen | geschätzt
2023-09-20 | 10 | GraphDB, RDF, Shactor, QSE | geschätzt |  | Row Labels | Sum of Stunden | Soll | minus
2023-10-03 | 1 | Meeting | geschätzt |  | Jän | 15 | 63 | -48
2023-10-05 | 3 | Einlesen | geschätzt |  | Feb | 3 | 0 | 3
2023-10-09 | 4 | QSE einlesen |  |  | Mär | 75 | 125 | -50
2023-10-10 | 3 | QSE einlesen |  |  | Apr | 57 | 125 | -68
2023-10-11 | 3 | QSE einlesen |  |  | Mai | 58 | 125 | -67
2023-10-13 | 4 | Diff Problem ansehen |  |  | Jun | 26 | 125 | -99
2023-10-15 | 8 | Knowledge graph VO ansehen |  |  | Aug | 6 | 0 | 0
2023-10-16 | 3 | Themen einschränken |  |  | Sep | 18 | 0 | 18
2023-10-20 | 4 | Graphversionierung recherchieren |  |  | Okt | 33 | 63 | -30
2023-11-04 | 2 | Mail schreiben |  |  | Nov | 48 | 63 | -15
2023-11-06 | 4 | Exposee anfangen, Design |  |  | Dez | 40 | 63 | -23
2023-11-09 | 2 | Design |  |  | Grand Total | 379
2023-11-10 | 4 | Design, Vaadin, RQ
2023-11-13 | 4 | Exposee
2023-11-14 | 1 | BEAR Lesen
2023-11-15 | 1 | BEAR lesen
2023-11-23 | 7 | Meeting planen, Js-Diff, Papers Methoden
2023-11-24 | 2 | Meeting
2023-11-27 | 4 | Projekt aufsetzen, Git
2023-11-28 | 7 | Proposal aufsetzen, WebApp weitermachen
2023-11-29 | 8 | Proposal goals algorithmic, state of the art, evaluation, difference algorithm finden (Jena difference)
2023-11-30 | 2 | Web Versionen
2023-12-04 | 5 | Proposal, Shapes generieren
2023-12-13 | 1 | Meeting Vorbereitung
2023-12-14 | 3 | Meeting Nachbereitung
2023-12-15 | 2 | Research questions
2023-12-20 | 4 | EKG Paper lesen
2023-12-22 | 4 | Website Shapes extrahieren
2023-12-27 | 5 | WebApp
2023-12-28 | 8 | WebApp Comparison Overview
2023-12-29 | 8 | WebApp Comparison Detail
2024-01-08 | 1 | Meeting
2024-01-10 | 7 | WebApp Graph/Version editable and deleteable, Ui adjustments, performance
2024-01-24 | 2 | Proposal
2024-01-25 | 1 | Proposal
2024-01-29 | 2 | Meeting + Proposal
2024-01-31 | 2 | Proposal
2024-02-02 | 3 | Proposal
2024-03-02 | 4 | Proposal
2024-03-05 | 2 | Webapp comparison for detail view property shapes
2024-03-05 | 3 | Propsoal
2024-03-05 | 3 | Bug Blank Nodes Anzeige
2024-03-06 | 3 | Bug Blank Nodes Anzeige
2024-03-06 | 5 | Filter Overview
2024-03-07 | 2 | Proposal
2024-03-08 | 3 | Navigation Session Variablen
2024-03-08 | 2 | Bugs fixen
2024-03-13 | 5 | Proposals Review
2024-03-15 | 2 | Ui fixes
2024-03-17 | 1 | Ui fixes
2024-03-18 | 2 | Meetings + VM
2024-03-19 | 3 | Presentation Vorb
2024-03-19 | 3 | Remove Supp and Conf, ShaclOrItems, Default Shapes saved
2024-03-20 | 8 | Bugs & why shapes have been added, deleted
2024-03-22 | 5 | Proposal Presentation
2024-03-26 | 8 | VM einrichten, WebApp testen mit echten Daten
2024-03-28 | 8 | Load pre-configured graphs, performance problems
2024-03-29 | 3 | Performance issues
2024-04-02 | 7 | Performance issues
2024-04-03 | 5 | Performance issues
2024-04-05 | 1 | RQ4 planen
2024-04-05 | 3 | Planen, Bugfixes
2024-04-09 | 1 | Meeting
2024-04-09 | 5 | Bugfixes
2024-04-12 | 3 | Bugfixes
2024-04-12 | 3 | Schreiben
2024-04-17 | 5 | RQ1 schreiben
2024-04-17 | 2 | QSE für Query Based probieren
2024-04-19 | 8 | RQ4 anfangen -> QSE QB geht nicht
2024-04-23 | 6 | QSE Bugfixes bei QueryBased, Vergleiche zwischen QB und FB
2024-04-24 | 6 | RQ4
2024-04-30 | 2 | RQ4
2024-05-03 | 5 | RQ4
2024-05-04 | 1 | RQ4
2024-05-07 | 5 | RQ4
2024-05-08 | 1 | Meeting
2024-05-08 | 4 | QSE Versionen ansehen
2024-05-10 | 1 | Methods schreiben
2024-05-11 | 1 | Related work schreiben
2024-05-14 | 3 | Related work schreiben
2024-05-14 | 4 | SLR
2024-05-15 | 8 | SLR
2024-05-17 | 3 | Kashif Fragen vorbereiten
2024-05-17 | 2 | Related work schreiben
2024-05-20 | 2 | Kashif Fragen
2024-05-20 | 2 | Related work schreiben
2024-05-22 | 3 | Related work, Architecture schreiben
2024-05-24 | 1 | Web-App Kapitel neu schreiben
2024-05-25 | 1 | Web-App Kapitel neu schreiben
2024-05-26 | 3 | Inital draft umschreiben
2024-05-27 | 1 | Inital draft umschreiben
2024-05-27 | 3 | Git fixen
2024-05-29 | 3 | Git fixen
2024-05-29 | 1 | RQ4
2024-06-03 | 2 | RQ4
2024-06-04 | 2 | RQ4
2024-06-04 | 3 | Geschriebenes kontrollieren
2024-06-04 | 3 | RQ4
2024-06-05 | 2 | RQ4 - or item ein item left, weiterschreiben
2024-06-06 | 3 | RQ4 - Comparison between two QSE runs
2024-06-10 | 5 | RQ4 - Comparison with Sparql, MetaComparator
2024-06-11 | 6 | RQ4 - OrItems bug, support pruning
2024-06-12 | 8 | RQ4 - auf VM einrichten, Graphdb installieren
2024-06-13 | 8 | RQ4 - QSE1 nur einmal ausführen, bugfixes undefined und 3,2^^kilometre, Meeting
2024-06-14 | 3 | RQ4 - Confidence+Pruning, Code Review
2024-06-17 | 2 | RQ4 Code Review, Tests fixen
2024-06-17 | 3 | Projekte mergen
2024-06-18 | 1 | Architektur so lassen, wie sie ist
2024-06-18 | 5 | RQ4 - remove mincount, Evaluation
2024-06-19 | 6 | RQ4 - Evaluation
2024-06-20 | 4 | RQ4 - Evaluation
2024-06-21 | 5 | RQ4 - Evaluation
2024-06-21 | 1 | Schreiben
2024-06-22 | 1 | Schreiben
2024-06-24 | 3 | Schreiben
2024-06-25 | 6 | Schreiben
2024-06-26 | 6 | Schreiben
2024-06-27 | 4 | Schreiben
2024-06-28 | 3 | Schreiben
2024-06-30 | 5 | Schreiben
2024-07-01 | 2 | Schreiben
2024-07-02 | 6 | Schreiben
2024-07-03 | 6 | Schreiben
2024-07-05 | 6 | Schreiben
2024-07-10 | 3 | Meeting, Schreiben
2024-07-15 | 3 | Schreiben
2024-07-16 | 5 | RQ2
2024-07-17 | 6 | RQ2
2024-07-19 | 6 | RQ2

## Zeitplan
Zeit | Aufgabe
2023-12-15 | Methoden, Titel, Papers
2023-01-15 | Research Methods Paper (Methoden)
2023-03-01 | Proposal Upload
2023-03-15 | Proposal Präsi
| schreiben | 2 Monate
Features jeweils 1 Monat
| Website | 2 Monate
1 Monat Spazi
Stand Anfang März
Website fertig + why shapes were added Ende - März
für jeden Algorithmus 1 Monat + 1 Monat Spazi = Ende Juli
Alles auf VM, testen, Experimente 2 Monate - Ende September
Experteninterviews 1 Monat - Ende Oktober
Schreiben: 2 Monate Ende 2024